## 15-Day Plan
Day | Focus | Concepts to Learn | Development Tasks | Deliverable | Git Milestone
0 | Project Planning | Requirements, Scope, Architecture | Create new GitHub repo, README, folder structure, wireframes, DB draft | Project initialized | Initial commit
1 | Frontend Setup | HTML Structure | Landing page, assets, navigation | Landing page | feat: landing
2 | Authentication UI | Forms, CSS | Register & Login pages | Auth UI | feat: auth-ui
3 | Dashboard UI | JS basics, Layout | Student dashboard static UI | Dashboard UI | feat: dashboard-ui
4 | Backend Setup | FastAPI, REST | Project structure, base APIs | Backend running | feat: backend-init
5 | Database | PostgreSQL, SQLAlchemy | Database models & connection | DB connected | feat: database
6 | Authentication Backend | JWT, Hashing | Register/Login APIs | Working auth | feat: authentication
7 | Projects Module | CRUD | Project APIs + frontend integration | Projects module | feat: projects
8 | Tasks Module | Relationships | Task CRUD + integration | Tasks module | feat: tasks
9 | Skills Module | CRUD | Skills CRUD + UI | Skills module | feat: skills
10 | Placements | CRUD, Filtering | Placement tracker | Placement module | feat: placements
11 | Dashboard Integration | Fetch API | Live dashboard statistics | Dynamic dashboard | feat: dashboard-data
12 | Validation | Error handling | Frontend/backend validation | Stable app | fix: validation
13 | Testing | Debugging | Full testing, bug fixes | Release candidate | release: rc1
14 | Deployment | Deployment | Deploy frontend/backend, screenshots | Live application | v1.0.0
15 | Documentation | README, Demo | Finalize README, architecture, demo video | Portfolio-ready project | docs: final