## 45-Day Roadmap
Day | Main Concept | Harsha | Srikar | Final Deliverable
1 | Architecture & Requirements | Frontend: Design pages, navigation flow, wireframes | Backend: Design modules, API flow, database requirements | Complete CampusHub architecture
2 | Git & GitHub | Backend: Create repository, folders, .gitignore, development setup | Frontend: Create README, page structure, frontend folders | Working repository
3 | Git Branches & PRs | Frontend: Create sample feature branch and change | Backend: Review PR, request changes, test merge workflow | First successful PR
4 | HTML Fundamentals | Backend: Study HTTP/backend role and prepare API requirements | Frontend: Build Landing page | Landing HTML
5 | HTML Forms | Frontend: Build Login page | Backend: Define registration/login request-response structure | Login structure + Auth API contract
6 | CSS Fundamentals | Backend: Learn Python project structure and prepare backend environment | Frontend: Style Landing and Login | Styled public pages
7 | CSS Grid & Flexbox | Frontend: Build Dashboard UI | Backend: Design dashboard API data requirements | Dashboard static UI + API contract
8 | JavaScript Fundamentals | Backend: Python functions/modules practice | Frontend: Add basic JS interactions | Interactive frontend
9 | DOM & Events | Frontend: Registration form DOM handling | Backend: Build temporary registration API logic | Registration frontend + temporary backend
10 | Fetch API | Backend: Create first FastAPI server | Frontend: Connect frontend to temporary API | First frontend-backend connection
11 | FastAPI Basics | Frontend: Build reusable frontend API helper functions | Backend: Build GET and POST routes | Basic API system
12 | HTTP & REST | Backend: Build Projects temporary REST API | Frontend: Build Projects static page | Project API + UI
13 | Pydantic | Frontend: Add frontend project form validation | Backend: Create Pydantic project schemas | Validated project requests
14 | SQL Fundamentals | Backend: Practice CREATE, INSERT, SELECT | Frontend: Build Project Details page | SQL practice + project details UI
15 | SQL CRUD | Frontend: Build Task UI | Backend: Practice UPDATE, DELETE, WHERE, ORDER BY | Task UI + SQL CRUD knowledge
16 | Database Relationships | Backend: Design users/projects/tasks relationships | Frontend: Build Skills page | ER design + Skills UI
17 | JOINs | Frontend: Build Placement Tracker page | Backend: Practice INNER JOIN and LEFT JOIN | Placement UI + JOIN practice
18 | PostgreSQL | Backend: Create users, projects, tasks tables | Frontend: Improve responsiveness of all current pages | Core database + responsive UI
19 | SQLAlchemy | Frontend: Build loading, success, and error UI states | Backend: Create User and Project models | ORM models
20 | Database Integration | Backend: Connect FastAPI to PostgreSQL | Frontend: Create frontend configuration/API utilities | Working DB connection
21 | Registration | Frontend: Connect registration form to API | Backend: Build registration API | Working registration
22 | Password Hashing | Backend: Implement secure password hashing | Frontend: Add registration validation/error handling | Secure registration
23 | Login | Frontend: Connect Login UI | Backend: Build credential verification | Working login
24 | JWT | Backend: Generate JWT access tokens | Frontend: Handle and store authentication token | JWT authentication
25 | Protected Routes | Frontend: Add protected-page logic and logout | Backend: Build current-user dependency and protected API | Protected application
26 | Authentication Testing | Backend: Fix authentication backend bugs | Frontend: Test complete auth UI flow | Stable authentication module
27 | Project CRUD | Frontend: Render projects dynamically | Backend: Build Create/Get Project APIs | Create and view projects
28 | Update & Delete | Backend: Build Update/Delete APIs | Frontend: Build edit/delete controls | Complete Project CRUD
29 | Project Integration | Frontend: Test and improve project UX | Backend: Ownership validation and backend fixes | Stable Projects module
30 | Task Relationships | Backend: Create Task model and project relationship | Frontend: Build dynamic task components | Task foundation
31 | Task CRUD | Frontend: Connect Create/Get Task UI | Backend: Build Create/Get Task APIs | Task creation and display
32 | Task Update/Delete | Backend: Build Update/Delete Task APIs | Frontend: Connect edit/delete UI | Complete Task CRUD
33 | Filtering | Frontend: Build filter and search UI | Backend: Build query parameters and filtering | Task filtering system
34 | Skills System | Backend: Create Skills and UserSkills models/APIs | Frontend: Connect Skills UI | Working Skills module
35 | Skills Integration | Frontend: Improve skills UX and dynamic rendering | Backend: Test relationships and fix Skills APIs | Stable Skills module
36 | Placement System | Backend: Create Company and Application models | Frontend: Connect Placement forms | Placement foundation
37 | Placement CRUD | Frontend: Dynamic placement rendering | Backend: Build complete Placement CRUD APIs | Placement CRUD
38 | Placement Filtering | Backend: Build status filtering/sorting | Frontend: Build filter controls and statistics UI | Complete Placement module
39 | SQL Aggregation | Frontend: Prepare Dashboard dynamic components | Backend: Build COUNT/GROUP BY statistics APIs | Dashboard data APIs
40 | Dashboard Integration | Backend: Optimize/fix dashboard APIs | Frontend: Connect dashboard to real data | Dynamic Dashboard
41 | Error Handling | Frontend: Improve errors, loading states, empty states | Backend: Add exception handling and API validation | Better user experience
42 | Testing & Security | Backend: Security review, environment variables, CORS | Frontend: Full application testing and bug reporting | Production-ready application
43 | Deployment | Frontend: Deploy frontend | Backend: Deploy FastAPI + PostgreSQL | Live CampusHub
44 | Documentation | Backend: API documentation and database diagram | Frontend: README, screenshots, UI documentation | Professional project documentation
45 | Final Review | Frontend: Explain and rebuild one frontend feature independently | Backend: Explain and rebuild one backend feature independently | Final evaluation + demo